## Year 1 work plan
Budget Year -1
Reference N. | Objective | Service Delivery Area (SDA) | Activity | Directly related indicator | Timing |  |  |  | Reference to Previous Rounds or Other Source of Funding | Responsible for Implementation | Implementing Entity Type
|  | SDA | Activity |  | Q1 | Q2 | Q3 | Q4
1.1.1 | 1 | ITN | Planning , Identification ,and prioritization of villages for LLIN, review of distribution and logistics supply management for LLIN distribution--Regional Consultation in NE region - Assam | N |  |  |  |  | No | PR1 | MoH
1.1.2 | 1 | ITN | Procurement of LLIN (centralized) | N |  |  |  |  | No | PR1 | MoH
1.1.3a | 1 | ITN | Supply of LLIN to state ( Principal Consignee) including handling charges | N |  |  |  |  | No | PR1 | MoH
1.1.3b | 1 | ITN | Renting of storage space for LLIN at state level | N |  |  |  |  | No | PR1 | MoH
1.1.3c | 1 | ITN | Renting of storage space for LLIN at district level | N |  |  |  |  | No | PR1 | MoH
1.1.3d | 1 | ITN | Logistics including transportation of LLIN from state to district | N |  |  |  |  | No | PR1 | MoH
1.1.3e | 1 | ITN | Logistics including transportation of LLIN from district to distribution points--village (inaccessible) in PR1 areas | N |  |  |  |  | No | PR1 | MoH
1.1.3f | 2 | ITN | Logistics including transportation of LLIN from district to distribution points--village in PR1 areas | N |  |  |  |  | No | PR1 | MoH
1.1.3g | 1 | ITN | Logistics including transportation of LLIN from district to distribution points--village (inaccessible) in PR2 areas | N |  |  |  |  | No | PR2 | FBO
1.1.3h | 1 | ITN | Logistics including transportation of LLIN from district to distribution points--village in PR2areas | N |  |  |  |  | No | PR2 | FBO
1.1.4 | 1 | ITN | BCC for community mobilization | [6 empty] | PR2 | FBO
1.1.5 | 1 | ITN | Trainings of ASHA, Volunteers, program/project personnel, at various levels | Detailed under Objective 3. SDA: BCC: Community outreach/IPC; SDA: BCC: Mass media
1.1.6a | 1 | ITN | LLIN distribution by ASHA/health worker, volunteer in PR1 areas [activities to include community mobilization through BCC (door to door IPC), distribution, recording on registers, preparation/transmission of report, etc.] | Y |  |  |  |  | No | PR1 | MoH
1.1.6b | 1 | ITN | LLIN distribution by ASHA/health worker, volunteer in PR2 areas [activities to include community mobilization through BCC (door to door IPC), distribution, recording on registers, preparation/transmission of report, etc.] | Y |  |  |  |  | No | PR1 | FBO
1.1.7 | 1 | ITN | M&E of distribution of LLIN | Y |  |  |  |  | No | PR1 | FBO
2.1.1 | 2 | Diagnosis | Planning ,Identification and prioritization of areas (villages, health Centres) for RDT, review of distribution and logistics supply management for RDT distribution--Regional Consultation in NE region - Assam | Detailed under Objective 5. SDA: HSS: Information system (M&E)
2.1.2 | 2 | Diagnosis | Procurement (centralized) of RDT | N |  |  |  |  | No | PR1 | MoH
2.1.3a | 2 | Diagnosis | Supply of RDT to state level ( Principal Consignee) includes handling charges | N |  |  |  |  | No | PR1 | MoH
2.1.3b | 2 | Diagnosis | Renting of storage space for RDT at state level | N |  |  |  |  | No | PR1 | MoH
2.1.3c | 2 | Diagnosis | Renting of storage space for RDT at district level | N |  |  |  |  | No | PR1 | MoH
2.1.3d | 2 | Diagnosis | Logistics including transportation of RDT from state to district | Clubbed with the Renting of storage space space for LLIN. Please see reference no. 1.1.3b
2.1.3e | 2 | Diagnosis | Logistics including transportation of RDT from district to distribution points--village/health centre | Clubbed with the Renting of storage space space for LLIN. Please see reference no. 1.1.3c
2.1.4 | 2 | Diagnosis | BCC for community mobilization | Clubbed with logistics including transportation of LLIN. Please see reference no. 1.1.3d
2.1.5 | 2 | Diagnosis | Trainings of ASHA. Volunteers, Health Workers, Program/project personnel at various levels | Clubbed with logistics including transportation of LLIN. Please see reference no. 1.1.3d
2.1.6 | 2 | Diagnosis | RDT use for diagnosis | Y |  |  |  |  | No | PR1 | MoH
2.1.7 | 2 | Diagnosis | M&E of RDT use | Detailed under Objective 4. SDA: HSS: Human resources (training/capacity building)
2.2.1 | 2 | Prompt, effective treatment | Planning ,Identification and prioritization of areas ( villages, health centres) for ACT, review of distribution and logistics supply management for ACT distribution--Regional Consultation in NE region - Assam | Y |  |  |  |  | No | PR1 | MoH
2.2.2a | 2 | Prompt, effective treatment | Procurement of ACT (blister packs for adults) [ centralized] | N |  |  |  |  | No | PR1 | MoH
2.2.2b | 2 | Prompt, effective treatment | Procurement of ACT (blister packs children) [ centralized] | N |  |  |  |  | No | PR1 | MoH
2.2.3a | 2 | Diagnosis | Supply of ACT to state level ( Principal Consignee) | N |  |  |  |  | No | PR1 | MoH
2.2.3b | 2 | Prompt, effective treatment | Renting of storage space for ACT at state level | N |  |  |  |  | No | PR1 | MoH
2.2.3c | 2 | Prompt, effective treatment | Renting of storage space of ACT at district level | N |  |  |  |  | No | PR1 | MoH
2.2.3d | 2 | Prompt, effective treatment | Logistics including transportation of ACT from state to district | N |  |  |  |  | No | PR1 | MoH
2.2.3e | 2 | Prompt, effective treatment | Logistics including transportation of ACT from district to distribution points--village, health centres | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.2.4 | 2 | Prompt, effective treatment | BCC for community mobilization | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.2.5 | 2 | Prompt, effective treatment | Trainings of concerned ASHA, Volunteers, program/project personnel, at various levels | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.2.6 | 2 | Prompt, effective treatment | ACT use for treatment | Clubbed with the storage space for LLIN. Please see reference no. 1.1.3b
2.2.7 | 2 | Prompt, effective treatment | M&E of ACT use | Clubbed with the storage space for LLIN. Please see reference no. 1.1.3c
2.3.1 | 2 | Prompt, effective treatment | Planning & Identification and prioritization of areas (Health Centres) for Injectable Artemisinin derivatives, review of distribution and logistics supply management , | Clubbed with logistics including transportation of LLIN. Please see reference no. 1.1.3d
2.3.2 | 2 | Prompt, effective treatment | Procurement of Injectable Artemisinin derivatives (centralized) | N |  |  |  |  | No | PR1 | MoH
2.3.3a | 2 | Prompt, effective treatment | Supply of Injectable Artemisinin derivatives to state | N |  |  |  |  | No | PR1 | MoH
2.3.3b | 2 | Prompt, effective treatment | Renting of storage space for Injectable Artemisinin derivatives at state level | Detailed under Objective 4. SDA: HSS: Human resources (training/capacity building)
2.3.3c | 2 | Prompt, effective treatment | Renting of storage space for Injectable Artemisinin derivatives at district level | Clubbed with RDT use by ASHA / Health worker
2.3.3d | 2 | Prompt, effective treatment | Logistics including transportation of Injectable Artemisinin derivatives from state to district | N |  |  |  |  | No | PR1 | MoH
2.3.3e | 2 | Prompt, effective treatment | Logistics including transportation of Injectable Artemisinin derivatives from district to distribution points--health centres | N |  |  |  |  | No | PR1 | MoH
2.3.4 | 2 | Prompt, effective treatment | BCC for community mobilization | Clubbed with state consultation for distribution of LLIN. Please see reference no. 1.1.1b
2.3.5 | 2 | Prompt, effective treatment | Trainings of medical/para medical personnel, in identified health centres; health workers/ASHAS.Volunteers; concerned program /project personnel at various levels | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.3.6 | 2 | Prompt, effective treatment | M&E | N |  |  |  |  | No | NVBDCP--PR1 | MoH
3.1.1 | 3 | BCC: Community outreach | Regional workshop for consolidating/fine tuning BCC strategy and operational plan, tools (community outreach/IPC/Mass Media) based on knowledge, materials with NVBDCP) | N |  |  |  |  | No | PR1 | MoH
3.1.2 | 3 | BCC: Community outreach | Workshop at district level for local adaptation of BCC tools including give away materials to support--community outreach/IPC (flip book, information card, infotainment script, illustrative leaflet/caps, other locally appropriate materials) | N |  |  |  |  | No | PR2 | FBO
3.1.3a | 3 | BCC: Community outreach | Translation of BCC tools including give away materials for community outreach/IPC in local language/dialect | N |  |  |  |  | No | PR2 | FBO
3.1.3b | 3 | BCC: Community outreach | Replication of BCC tools for community outreach/IPC--flip book / Information card / Infotainment script / other locally appropriate material | N |  |  |  |  | No | PR2 | FBO
3.1.3c | 3 | BCC: Community outreach | Replication of BCC materials for community outreach/IPC--illustrative leaflet , caps other locally appropriate material a | N |  |  |  |  | No | PR2 | FBO
3.1.3d | 3 | BCC: Community outreach | Logistics including transportation for dissemination of BCC tools, give away materials to distribution points--volunteer/ASHA/health worker/other BCC outlets in village/blocks/districts | N |  |  |  |  | No | PR2 | FBO
3.1.4a | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through - Community outreach activities -- facilitating organization of infotainment (folk medium, etc) and/or conducting group meeting and dissemination of BCC give away materials, miking during high transmission season (3 months), preparing/transmitting report in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4b | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through - Community outreach activities -- facilitating organization of infotainment (folk medium, etc) and/or conducting group meeting and dissemination of BCC give away materials, miking during high transmission season (3 months), preparing/transmitting report in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4c | 3 | BCC: Community outreach | Infotainment performance by local group in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4d | 3 | BCC: Community outreach | Infotainment performance by local group in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4e | 3 | BCC: Community outreach | Miking during high transmission season in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4f | 3 | BCC: Community outreach | Miking during high transmission season in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4g | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through IPC and dissemination of BCC give away materials in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4h | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through IPC and dissemination of BCC give away materials in PR2 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4i | 3 | BCC: Community outreach | Local school activity for dissemination of messages, preparing / transmitting report in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4j | 3 | BCC: Community outreach | Local school activity for dissemination of messages, preparing / transmitting report in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4k | 3 | BCC: Community outreach | Wall writing in local language in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4l | 3 | BCC: Community outreach | Wall writing in local language in PR2 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4m | 4 | Coordination and Partnership development | Community message dissemination in PR1 areas | Y |  |  |  |  | No | PR1 | MoH
3.1.4n | 4 | Coordination and Partnership development | Community message dissemination in PR2 areas | Y |  |  |  |  | No | PR2 | FBO
3.1.5 | 3 | BCC: Community outreach | Trainings of ASHA, Volunteers, concerned medical/paramedical/program/project personnel, at various levels | N |  |  |  |  | No | PR2 | FBO
3.1.6 | 3 | BCC: Community outreach | M&E of BCC | [5 empty] | No | PR1 | MoH
3.2.1 | 3 | BCC: mass media | Regional workshop for consolidating/fine tuning BCC strategy and operational plan, tools (Mass Media) based on knowledge, materials with NVBDCP) | N |  |  |  |  | No | PR1 | MoH
3.2.2 | 3 | BCC: mass media | Workshop at district level for local adaptation of mass media messages , materials (radio) | N |  |  |  |  | No | PR2 | FBO
3.2.3 | 3 | BCC: mass media | Dubbing of mass media messages in the local languages | N |  |  |  |  | No | PR1 | MoH
3.2.4 | 3 | BCC: mass media | BCC - mass media implementation - skit/jingle on Radio | N |  |  |  |  | No | PR1 | MoH
3.2.5 | 3 | BCC: mass media | M&E of BCC | Detailed under Objective 4. SDA: HSS: Human resources (training/capacity building)
4.1.1 | 4 | HSS: Human resources- Health Work Force | Recruitment of Teams for Technical & Management assistance , M & E assistance ,planning and administration assistance at national , regional , state , district levels
4.1.1a | 4 | HSS: Human resources- Health Work Force | TA through WHO to PR1 at national level ( refer to annexure worksheet) | N |  |  |  |  | No | PR1 | MoH
4.1.1b | 4 | HSS: Human resources- Health Work Force | National level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR1
i | 4 | HSS: Human resources- Health Work Force | Finance & Accounts officer (1) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | Accounts assistant (1) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Computer Programmer--NAMMIS, software, hardware (1) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | Statistician (1) | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | Secretarial Assistants (3) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | Data entry operators (2) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-Laptop with all necessary software and data card(5) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and equipment - Desktop with all with all necessary software and broadband connection (5) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Furniture etc.. | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Office infrastructure and Equipment -office automation unit -- printer(1), copier (1), fax (1) , Scanner (1) | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Office Expenses - Documentation and printing | N |  |  |  |  | No | PR1 | MoH
xii | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other equipments | N |  |  |  |  | No | PR1 | MoH
4.1.1c | 4 | HSS: Human resources- Health Work Force | Regional Resource Team with PR1
i | 4 | HSS: Human resources- Health Work Force | Specialist--Public Health (1) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | Specialist--Entomology (1) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Specialist--M&E/MIS, QA, operations research (1) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | Specialist--BCC, Public Private Partnership (1) | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | Specialist--Training (1) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | Administrative officer (1) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | Accountant (1) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Statistician (1) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Data manager including GIS (1) | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Data entry operator(1) | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant(1) | N |  |  |  |  | No | PR1 | MoH
xii | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR1 | MoH
xiii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-Laptop with all necessary software and data card (5) | N |  |  |  |  | No | PR1 | MoH
xiv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-Desktop with all with all necessary software and broadband connection (2) | N |  |  |  |  | No | PR1 | MoH
xv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment (furniture etc) | N |  |  |  |  | No | PR1 | MoH
xvi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-office automation units--printer(1), copier (1), fax (1) , Scanner (1) ,Telephone with intercom facility (5) | N |  |  |  |  | No | PR1 | MoH
xvii | 4 | HSS: Human resources- Health Work Force | Office expenses--Documentation and printing | N |  |  |  |  | No | PR1 | MoH
xviii | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR1 | MoH
xix | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other equipments | N |  |  |  |  | No | PR1 | MoH
4.1.1d | 4 | HSS: Human resources- Health Work Force | State level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR1
I | 4 | HSS: Human resources- Health Work Force | VBD Project Manager(7) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | M&E / MIS Project Manager(7) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | BCC/PPP Manager(7) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | PSCM manager (7) | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | · Finance and accounts officer (7) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | · Statistical assistant (7) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | · Secretarial Assistant (14) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Laptop with all necessary software and data card | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -Desktop with all with all necessary software and broadband connection (3) | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) Telephone with intercom facility (5) | N |  |  |  |  | No | PR1 | MoH
xii | 4 | HSS: Human resources- Health Work Force | Office Expenses - Documentation and printing | N |  |  |  |  | No | PR1 | MoH
xiii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment (furniture etc...) | N |  |  |  |  | No | PR1 | MoH
xiv | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR1 | MoH
xv | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other office equipments | N |  |  |  |  | No | PR1 | MoH
4.1.1e | 4 | HSS: Human resources- Health Work Force | District level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR1
i | 4 | HSS: Human resources- Health Work Force | District VBD (Malaria) Project Officer (86) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | MTS (258) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant cum Data entry operator (86) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Mobility Provision | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure - Laptop with all necessary software and data card (86) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Desktop with all with all necessary software and broadband connection (86) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment --Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) Telephone with intercom facility (1) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office Expense - Documentation and printing | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Office infrastructure and Equipment ( furniture..) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Office Expenses -- Maintenance of IT equipment and other equipment | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Lab Technician (62) | N |  |  |  |  | No | PR1 | MoH
4.1.1f | 4 | HSS: Human resources- Health Work Force | Sentinel Surveillance Team
i | 4 | HSS: Human resources- Health Work Force | Nodal Officer at Sentinel Site (13) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | Lab Technician at sentinel Site (13) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Office infrastructure and Equipments and Office expenses | N |  |  |  |  | No | PR1 | MoH
4.1.1g | 4 | HSS: Human resources- Health Work Force | National level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR2 & SRs
I | 4 | HSS: Human resources- Health Work Force | Team leader (1) | N |  |  |  |  | No | PR2 | FBO
ii | 4 | HSS: Human resources- Health Work Force | Manager—Technical (1) | N |  |  |  |  | No | PR2 | FBO
iii | 4 | HSS: Human resources- Health Work Force | Manager—Grant (1) | N |  |  |  |  | No | PR2 | FBO
iv | 4 | HSS: Human resources- Health Work Force | Manager Short Term --GFATM (3) [Short term--60 days in a year] | N |  |  |  |  | No | PR2 | FBO
v | 4 | HSS: Human resources- Health Work Force | Expert—M&E (1) | N |  |  |  |  | No | PR2 | FBO
vi | 4 | HSS: Human resources- Health Work Force | · Expert--MIS (1) [Part Time--120 days in a year] | N |  |  |  |  | No | PR2 | FBO
vii | 4 | HSS: Human resources- Health Work Force | · Expert—Training (1) | N |  |  |  |  | No | PR2 | FBO
viii | 4 | HSS: Human resources- Health Work Force | Technical Expert (2) [Short Term --240 days in a year] | N |  |  |  |  | No | PR2 | FBO
ix | 4 | HSS: Human resources- Health Work Force | Communication officer (1) | N |  |  |  |  | No | PR2 | FBO
x | 4 | HSS: Human resources- Health Work Force | Finance and accounts officer (1) | N |  |  |  |  | No | PR2 | FBO
xi | 4 | HSS: Human resources- Health Work Force | Data and documentation officer (4) | N |  |  |  |  | No | PR2 | FBO
xii | 4 | HSS: Human resources- Health Work Force | Data entry operator (2) | N |  |  |  |  | No | PR2 | FBO
xiii | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant (4) | N |  |  |  |  | No | PR2 | FBO
xiv | 4 | HSS: Human resources- Health Work Force | Travel etc (inter-city within country) for Team leader (once in three months) | N |  |  |  |  | No | PR2 | FBO
xv | 4 | HSS: Human resources- Health Work Force | Travel (out station--inter-city/inter-state within country) for project staff (2 consultants at a time once a month) | N |  |  |  |  | No | PR2 | FBO
xvi | 4 | HSS: Human resources- Health Work Force | Travel (international) for attending international meeting, workshop etc of GFATM and its partners 2 person X 2 per year | N |  |  |  |  | No | PR2 | FBO
xvii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Laptop with all necessary software and data card (5) | N |  |  |  |  | No | PR2 | FBO
xviii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Desktop with all with all necessary software and broadband connection (5) | N |  |  |  |  | No | PR2 | FBO
xix | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment (furniture etc..) and Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) and telephone facilities | N |  |  |  |  | No | PR2 | FBO
xx | 4 | HSS: Human resources- Health Work Force | Office Expenses --Documentation and printing | N |  |  |  |  | No | PR2 | FBO
xxi | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables etc. | N |  |  |  |  | No | PR2 | FBO
xxii | 4 | HSS: Human resources- Health Work Force | Office Expenses -- Maintenance of IT equipment and other office equipment | N |  |  |  |  | No | PR2 | FBO
4.1.1h | 4 | HSS: Human resources- Health Work Force | Regional level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR2 & SRs
I | 4 | HSS: Human resources- Health Work Force | Project Manager (4—one each for PR2, SR1, SR2, SR3) | N |  |  |  |  | No | PR2 | FBO
ii | 4 | HSS: Human resources- Health Work Force | Project Officer (4—one each for PR2, SR1, SR2, SR3) | N |  |  |  |  | No | PR2 | FBO
iii | 4 | HSS: Human resources- Health Work Force | Finance & Accounts manager (4) | N |  |  |  |  | No | PR2 | FBO
iv | 4 | HSS: Human resources- Health Work Force | Logistics & SCM manager (1) | N |  |  |  |  | No | PR2 | FBO
v | 4 | HSS: Human resources- Health Work Force | M&E/MIS manager (1) | N |  |  |  |  | No | PR2 | FBO
vi | 4 | HSS: Human resources- Health Work Force | BCC/PPP manager (4) | N |  |  |  |  | No | PR2 | FBO
vii | 4 | HSS: Human resources- Health Work Force | Capacity building/Training manager (1) | N |  |  |  |  | No | PR2 | FBO
viii | 4 | HSS: Human resources- Health Work Force | Data and documentation officer (4) | N |  |  |  |  | No | PR2 | FBO
ix | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant cum Data entry operator (8) | N |  |  |  |  | No | PR2 | FBO
x | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR2 | FBO
xi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -- Laptop with all necessary software and data card (15) | N |  |  |  |  | No | PR2 | FBO
xii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -- Desktop with all with all necessary software and broadband connection (15) | N |  |  |  |  | No | PR2 | FBO
xiii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment (furniture.. ) , Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) Office automation units (5)and Telephone with intercom facility | N |  |  |  |  | No | PR2 | FBO
xiv | 4 | HSS: Human resources- Health Work Force | Office Expenses --Documentation and printing | N |  |  |  |  | No | PR2 | FBO
xv | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR2 | FBO
xvi | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other office equipments | N |  |  |  |  | No | PR2 | FBO
4.1.1i | 4 | HSS: Human resources- Health Work Force | District level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR2 & SRs
i | 4 | HSS: Human resources- Health Work Force | Project Officer (24) | N |  |  |  |  | No | PR2 | FBO
ii | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant cumData entry operator (24) | N |  |  |  |  | No | PR2 | FBO
iii | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR2 | FBO
iv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -- Laptop with all necessary software and data card | N |  |  |  |  | No | PR2 | FBO
v | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment --\Desktop with all with all necessary software and broadband connection | N |  |  |  |  | No | PR2 | FBO
vi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment furniture etc , Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1), Telephone with intercom facility | N |  |  |  |  | No | PR2 | FBO
vii | 4 | HSS: Human resources- Health Work Force | Office Expenses--Documentation and printing | N |  |  |  |  | No | PR2 | FBO
viii | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR2 | FBO
ix | 4 | HSS: Human resources- Health Work Force | Office Expense - Maintenance of IT equipment and other office equipment | N |  |  |  |  | No | PR2 | FBO
4.2.1 | 4 | HSS : Information System (M&E / MIS) | Regional consultation for consolidation and fine tuning of one M&E plan | N |  |  |  |  | No | PR1 | MoH
4.2.2a | 4 | HSS : Information System (M&E / MIS) | Integration of M&E Plan and performance monitoring for PR2 : consultation | N |  |  |  |  | No | PR2 | FBO
4.2.2b | 4 | HSS : Information System (M&E / MIS) | Development of MIS for PR2 performance reporting analysis and feed back to GFATM / Stakeholders | [5 empty] | No | PR1 | MoH
4.2.3a | 4 | HSS : Information System (M&E / MIS) | Printing and disseminations of M&E / MIS plan , guidelines , formats , check list to PR1 stakeholders | N |  |  |  |  | No | PR1 | MoH
4.2.3b | 4 | HSS : Information System (M&E / MIS) | Printing and disseminations of M&E / MIS plan , guidelines , formats , check list to PR2 stakeholders | N |  |  |  |  | No | PR2 | FBO
4.2.4 | 4 | HSS : Information System (M&E / MIS) | Training of M&E | N |  |  |  |  | No | PR2 | FBO
4.2.5a | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 national team in PR1 areas | [5 empty] | No | PR1 | MoH
4.2.5b | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 by Regional team in PR1 areas | N |  |  |  |  | No | PR1 | MoH
4.2.5c | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 states team in PR1 areas | N |  |  |  |  | No | PR2 | FBO
4.2.5d | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 district team - VBD project officer / MTS in PR1 areas | N | [5 empty] | PR2 | FBO
4.2.5e | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR2 national team in PR2 areas | N | [5 empty] | PR2 | FBO
4.2.5f | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR2 by Regional team in PR2 areas | N |  |  |  |  | No | PR1 | MoH
4.2.5g | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR2 district team in PR2 areas | N |  |  |  |  | No | PR1 | MoH
4.2.6a | 4 | HSS : Information System (M&E / MIS) | Annual planning and review meeting at national level with regional and state teams and other stakeholders -- PR1 | N |  |  |  |  | No | PR1 | MoH
4.2.6b | 4 | HSS : Information System (M&E / MIS) | Annual Planning and review meeting at state level with districts , other stakeholders -- PR1 | N |  |  |  |  | No | PR1 | MoH
4.2.6c | 4 | HSS : Information System (M&E / MIS) | Quarterly planning and review meeting at districts level with stakeholders -- PR1 | N |  |  |  |  | No | PR1 | MoH
4.2.6d | 4 | HSS : Information System (M&E / MIS) | Annual Planning and Review Meeting at National level with regional ,SRs ,other stakeholders -- PR2 | N |  |  |  |  | No | PR2 | FBO
4.2.6e | 4 | HSS : Information System (M&E / MIS) | Quarterly planning and Review Meeting at districts level with Stakeholders -- PR2 | N |  |  |  |  | No | PR2 | FBO
4.2.7 | 4 | HSS : Information System (M&E / MIS) | Lot Quality Assurance Sampling (LQAS) | N | [5 empty] | PR1 | MoH
4.2.8 | 4 | HSS : Information System (M&E / MIS) | Large Scale Population and house hold survey | N |  |  |  |  | No | PR1 | MoH
4.2.9 | 4 | HSS : Information System (M&E / MIS) | Evaluation by Independent agency | N |  |  |  |  | No | PR1 | MoH
4.2.10 | 4 | HSS : Information System (M&E / MIS) | Joint programme review by Mission | N |  |  |  |  | No | PR1 | MoH
4.2.11 | 4 | HSS : Information System (M&E / MIS) | Production of annual programme report and dissemination to stakeholders | N |  |  |  |  | No | PR1 | MoH
4.2.12 | 4 | HSS : Information System (M&E / MIS) | Operational Research | N |  |  |  |  | No | PR1 | MoH
4.2.13a | 4 | HSS : Information System (M&E / MIS) | Sentinel Surveillance- Training of Medical & para medical personnel | [6 empty] | PR1 | MoH
4.2.13b | 4 | HSS : Information System (M&E / MIS) | Sentinel Surveillance support for reporting of severe cases and deaths | [5 empty] | No | PR1 | MoH
4.3.1 | 4 | Coordination and Partnership development | National level consultation on coordination and partnership building with other departments/ Porgramme of MOHFW , #n health ministries / departments , NGO / FBO , Private sector , etc. | N |  |  |  |  | No | PR1 | MoH
4.3.2 | 4 | Coordination and Partnership development | One on one meeting with armed and para military forces , other non health ministries / dep't , municipal corporations , private sector ,PSU, NGO / FBO for partnership and MOU under PPP | N |  |  |  |  | No | PR1 | MoH
4.3.3 | 4 | Coordination and Partnership development | Inter Ministerial meeting on observance of anti-malaria month | N | [5 empty] | PR1 | MoH
4.3.4 | 4 | Coordination and Partnership development | Regional level workshop on coordination and partnership building with non health ministries / departments ,PSU , NGO / FBO , Private sector , etc. | N |  |  |  |  | No | PR1 | MoH
4.3.5 | 4 | Coordination and Partnership development | Inter Country Meeting on Border Malaria Issues | N |  |  |  |  | No | PR1 | MoH
4.3.6 | 4 | Coordination and Partnership development | Development & dissemination of newsletters | N |  |  |  |  | No | PR2 | FBO
5.1.1a | 5 | HSS: Human resources Training / Capacity Building | Induction Training of National , State level teams of PR1 at national level | N |  |  |  |  | No | PR1 | MoH
5.1.1b | 5 | HSS: Human resources Training / Capacity Building | Induction Training of National , Regional level teams of PR2 & SRs at national level | N |  |  |  |  | No | PR2 | FBO
5.1.1c | 5 | HSS: Human resources Training / Capacity Building | Induction Training of District level teams of PR2 & SRs at regional level | N |  |  |  |  | No | PR2 | FBO
5.1.2a | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of National , State level teams of PR1 at national level | N |  |  |  |  | No | PR1 | MoH
5.1.2b | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of National , Regional level teams of PR2 & SRs at national level | N |  |  |  |  | No | PR2 | FBO
5.1.2c | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of District level teams of PR2 & SRs at regional level | N |  |  |  |  | No | PR2 | FBO
5.1.3 | 5 | HSS: Human resources Training / Capacity Building | Training of National level programme personnel , consultant with PR1 co-managing GFATM grant on management | N |  |  |  |  | No | PR1 | MoH
5.1.4 | 5 | HSS: Human resources Training / Capacity Building | Induction training of District VBD (Malaria) Project Officer at national level | N |  |  |  |  | No | PR1 | MoH
5.1.5 | 5 | HSS: Human resources Training / Capacity Building | Refresher training of District VBD (Malaria) Project Officer at regional level | N |  |  |  |  | No | PR1 | MoH
5.1.6 | 5 | HSS: Human resources Training / Capacity Building | Induction Training of MTS | N |  |  |  |  | No | PR1 | MoH
5.1.7 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of MTS | N |  |  |  |  | No | PR1 | MoH
5.1.8 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of Medial Officer from referral health unit on management of severe malaria | N |  |  |  |  | No | PR1 | MoH
5.1.9 | 5 | HSS: Human resources Training / Capacity Building | Training Medical and para medical (LT) personnel in Sentinel surveillance sites on surveillance , data reporting / management | N |  |  |  |  | No | PR1 | MoH
5.1.10 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training for Medical Officers at Block PHC / PHC / CHC ; sub district health unit with PR2 | N |  |  |  |  | No | PR1 | MoH
5.1.11 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training for Lab. Technicians | N |  |  |  |  | No | PR1 | MoH
5.1.12a | 5 | HSS: Human resources Training / Capacity Building | Revisiting existing training modules for ASHA / Volunteers , customization, translationin | N |  |  |  |  | No | PR2 | FBO
5.1.12b | 5 | HSS: Human resources Training / Capacity Building | Replication and dissemination of training modules for ASHA / Volunteers | N |  |  |  |  | No | PR2 | FBO
5.1.13 | 5 | HSS: Human resources Training / Capacity Building | Training of ASHA / Volunteer | Y |  |  |  |  | No | PR2 | FBO
5.1.14a | 5 | HSS: Human resources Training / Capacity Building | Revisiting, customization, translation existing guidelines and development of training modules for private sector service provider | N |  |  |  |  | No | PR2 | FBO
5.1.14b | 5 | HSS: Human resources Training / Capacity Building | Replication and dissemination of existing modules for private sector service providers training at regional level | N |  |  |  |  | No | PR2 | FBO
5.1.15a | 5 | HSS: Human resources Training / Capacity Building | Mapping and training private sector service providers according to qualifications at block level in PR1 and PR2 areas | N |  |  |  |  | No | PR2 | FBO
5.1.15b | 5 | HSS: Human resources Training / Capacity Building | Mapping and training private sector service providers according to qualifications at District level in PR1 and PR2 areas | N |  |  |  |  | No | PR2 | FBO

## Year 2 work plan
Budget Year -1
Reference N. | Objective | Service Delivery Area (SDA) | Activity | Directly related indicator | Timing |  |  |  | Reference to Previous Rounds or Other Source of Funding | Responsible for Implementation | Implementing Entity Type
|  | SDA | Activity |  | Q1 | Q2 | Q3 | Q4
1.1.1 | 1 | ITN | Planning , Identification ,and prioritization of villages for LLIN, review of distribution and logistics supply management for LLIN distribution--Regional Consultation in NE region - Assam | N |  |  |  |  | No | PR1 | MoH
1.1.2 | 1 | ITN | Procurement of LLIN (centralized) | N |  |  |  |  | No | PR1 | MoH
1.1.3a | 1 | ITN | Supply of LLIN to state ( Principal Consignee) including handling charges | N |  |  |  |  | No | PR1 | MoH
1.1.3b | 1 | ITN | Renting of storage space for LLIN at state level | N |  |  |  |  | No | PR1 | MoH
1.1.3c | 1 | ITN | Renting of storage space for LLIN at district level | N |  |  |  |  | No | PR1 | MoH
1.1.3d | 1 | ITN | Logistics including transportation of LLIN from state to district | N |  |  |  |  | No | PR1 | MoH
1.1.3e | 1 | ITN | Logistics including transportation of LLIN from district to distribution points--village (inaccessible) in PR1 areas | N |  |  |  |  | No | PR1 | MoH
1.1.3f | 2 | ITN | Logistics including transportation of LLIN from district to distribution points--village in PR1 areas | N |  |  |  |  | No | PR1 | MoH
1.1.3g | 1 | ITN | Logistics including transportation of LLIN from district to distribution points--village (inaccessible) in PR2 areas | N |  |  |  |  | No | PR2 | FBO
1.1.3h | 1 | ITN | Logistics including transportation of LLIN from district to distribution points--village in PR2areas | N |  |  |  |  | No | PR2 | FBO
1.1.4 | 1 | ITN | BCC for community mobilization | [6 empty] | PR2 | FBO
1.1.5 | 1 | ITN | Trainings of ASHA, Volunteers, program/project personnel, at various levels | Detailed under Objective 3. SDA: BCC: Community outreach/IPC; SDA: BCC: Mass media
1.1.6a | 1 | ITN | LLIN distribution by ASHA/health worker, volunteer in PR1 areas [activities to include community mobilization through BCC (door to door IPC), distribution, recording on registers, preparation/transmission of report, etc.] | Y |  |  |  |  | No | PR1 | MoH
1.1.6b | 1 | ITN | LLIN distribution by ASHA/health worker, volunteer in PR2 areas [activities to include community mobilization through BCC (door to door IPC), distribution, recording on registers, preparation/transmission of report, etc.] | Y |  |  |  |  | No | PR1 | FBO
1.1.7 | 1 | ITN | M&E of distribution of LLIN | Y |  |  |  |  | No | PR1 | FBO
2.1.1 | 2 | Diagnosis | Planning ,Identification and prioritization of areas (villages, health Centres) for RDT, review of distribution and logistics supply management for RDT distribution--Regional Consultation in NE region - Assam | Detailed under Objective 5. SDA: HSS: Information system (M&E)
2.1.2 | 2 | Diagnosis | Procurement (centralized) of RDT | N |  |  |  |  | No | PR1 | MoH
2.1.3a | 2 | Diagnosis | Supply of RDT to state level ( Principal Consignee) includes handling charges | N |  |  |  |  | No | PR1 | MoH
2.1.3b | 2 | Diagnosis | Renting of storage space for RDT at state level | N |  |  |  |  | No | PR1 | MoH
2.1.3c | 2 | Diagnosis | Renting of storage space for RDT at district level | N |  |  |  |  | No | PR1 | MoH
2.1.3d | 2 | Diagnosis | Logistics including transportation of RDT from state to district | Clubbed with the Renting of storage space space for LLIN. Please see reference no. 1.1.3b
2.1.3e | 2 | Diagnosis | Logistics including transportation of RDT from district to distribution points--village/health centre | Clubbed with the Renting of storage space space for LLIN. Please see reference no. 1.1.3c
2.1.4 | 2 | Diagnosis | BCC for community mobilization | Clubbed with logistics including transportation of LLIN. Please see reference no. 1.1.3d
2.1.5 | 2 | Diagnosis | Trainings of ASHA. Volunteers, Health Workers, Program/project personnel at various levels | Clubbed with logistics including transportation of LLIN. Please see reference no. 1.1.3d
2.1.6 | 2 | Diagnosis | RDT use for diagnosis | Y |  |  |  |  | No | PR1 | MoH
2.1.7 | 2 | Diagnosis | M&E of RDT use | Detailed under Objective 4. SDA: HSS: Human resources (training/capacity building)
2.2.1 | 2 | Prompt, effective treatment | Planning ,Identification and prioritization of areas ( villages, health centres) for ACT, review of distribution and logistics supply management for ACT distribution--Regional Consultation in NE region - Assam | Y |  |  |  |  | No | PR1 | MoH
2.2.2a | 2 | Prompt, effective treatment | Procurement of ACT (blister packs for adults) [ centralized] | N |  |  |  |  | No | PR1 | MoH
2.2.2b | 2 | Prompt, effective treatment | Procurement of ACT (blister packs children) [ centralized] | N |  |  |  |  | No | PR1 | MoH
2.2.3a | 2 | Diagnosis | Supply of ACT to state level ( Principal Consignee) | N |  |  |  |  | No | PR1 | MoH
2.2.3b | 2 | Prompt, effective treatment | Renting of storage space for ACT at state level | N |  |  |  |  | No | PR1 | MoH
2.2.3c | 2 | Prompt, effective treatment | Renting of storage space of ACT at district level | N |  |  |  |  | No | PR1 | MoH
2.2.3d | 2 | Prompt, effective treatment | Logistics including transportation of ACT from state to district | N |  |  |  |  | No | PR1 | MoH
2.2.3e | 2 | Prompt, effective treatment | Logistics including transportation of ACT from district to distribution points--village, health centres | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.2.4 | 2 | Prompt, effective treatment | BCC for community mobilization | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.2.5 | 2 | Prompt, effective treatment | Trainings of concerned ASHA, Volunteers, program/project personnel, at various levels | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.2.6 | 2 | Prompt, effective treatment | ACT use for treatment | Clubbed with the storage space for LLIN. Please see reference no. 1.1.3b
2.2.7 | 2 | Prompt, effective treatment | M&E of ACT use | Clubbed with the storage space for LLIN. Please see reference no. 1.1.3c
2.3.1 | 2 | Prompt, effective treatment | Planning & Identification and prioritization of areas (Health Centres) for Injectable Artemisinin derivatives, review of distribution and logistics supply management , | Clubbed with logistics including transportation of LLIN. Please see reference no. 1.1.3d
2.3.2 | 2 | Prompt, effective treatment | Procurement of Injectable Artemisinin derivatives (centralized) | N |  |  |  |  | No | PR1 | MoH
2.3.3a | 2 | Prompt, effective treatment | Supply of Injectable Artemisinin derivatives to state | N |  |  |  |  | No | PR1 | MoH
2.3.3b | 2 | Prompt, effective treatment | Renting of storage space for Injectable Artemisinin derivatives at state level | Detailed under Objective 4. SDA: HSS: Human resources (training/capacity building)
2.3.3c | 2 | Prompt, effective treatment | Renting of storage space for Injectable Artemisinin derivatives at district level | Clubbed with RDT use by ASHA / Health worker
2.3.3d | 2 | Prompt, effective treatment | Logistics including transportation of Injectable Artemisinin derivatives from state to district | N |  |  |  |  | No | PR1 | MoH
2.3.3e | 2 | Prompt, effective treatment | Logistics including transportation of Injectable Artemisinin derivatives from district to distribution points--health centres | N |  |  |  |  | No | PR1 | MoH
2.3.4 | 2 | Prompt, effective treatment | BCC for community mobilization | Clubbed with state consultation for distribution of LLIN. Please see reference no. 1.1.1b
2.3.5 | 2 | Prompt, effective treatment | Trainings of medical/para medical personnel, in identified health centres; health workers/ASHAS.Volunteers; concerned program /project personnel at various levels | N |  |  |  |  | No | NVBDCP--PR1 | MoH
2.3.6 | 2 | Prompt, effective treatment | M&E | N |  |  |  |  | No | NVBDCP--PR1 | MoH
3.1.1 | 3 | BCC: Community outreach | Regional workshop for consolidating/fine tuning BCC strategy and operational plan, tools (community outreach/IPC/Mass Media) based on knowledge, materials with NVBDCP) | N |  |  |  |  | No | PR1 | MoH
3.1.2 | 3 | BCC: Community outreach | Workshop at district level for local adaptation of BCC tools including give away materials to support--community outreach/IPC (flip book, information card, infotainment script, illustrative leaflet/caps, other locally appropriate materials) | N |  |  |  |  | No | PR2 | FBO
3.1.3a | 3 | BCC: Community outreach | Translation of BCC tools including give away materials for community outreach/IPC in local language/dialect | N |  |  |  |  | No | PR2 | FBO
3.1.3b | 3 | BCC: Community outreach | Replication of BCC tools for community outreach/IPC--flip book / Information card / Infotainment script / other locally appropriate material | N |  |  |  |  | No | PR2 | FBO
3.1.3c | 3 | BCC: Community outreach | Replication of BCC materials for community outreach/IPC--illustrative leaflet , caps other locally appropriate material a | N |  |  |  |  | No | PR2 | FBO
3.1.3d | 3 | BCC: Community outreach | Logistics including transportation for dissemination of BCC tools, give away materials to distribution points--volunteer/ASHA/health worker/other BCC outlets in village/blocks/districts | N |  |  |  |  | No | PR2 | FBO
3.1.4a | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through - Community outreach activities -- facilitating organization of infotainment (folk medium, etc) and/or conducting group meeting and dissemination of BCC give away materials, miking during high transmission season (3 months), preparing/transmitting report in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4b | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through - Community outreach activities -- facilitating organization of infotainment (folk medium, etc) and/or conducting group meeting and dissemination of BCC give away materials, miking during high transmission season (3 months), preparing/transmitting report in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4c | 3 | BCC: Community outreach | Infotainment performance by local group in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4d | 3 | BCC: Community outreach | Infotainment performance by local group in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4e | 3 | BCC: Community outreach | Miking during high transmission season in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4f | 3 | BCC: Community outreach | Miking during high transmission season in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4g | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through IPC and dissemination of BCC give away materials in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4h | 3 | BCC: Community outreach | BCC implementation by ASHA/health worker/volunteer through IPC and dissemination of BCC give away materials in PR2 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4i | 3 | BCC: Community outreach | Local school activity for dissemination of messages, preparing / transmitting report in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4j | 3 | BCC: Community outreach | Local school activity for dissemination of messages, preparing / transmitting report in PR2 areas | N |  |  |  |  | No | PR2 | FBO
3.1.4k | 3 | BCC: Community outreach | Wall writing in local language in PR1 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4l | 3 | BCC: Community outreach | Wall writing in local language in PR2 areas | N |  |  |  |  | No | PR1 | MoH
3.1.4m | 4 | Coordination and Partnership development | Community message dissemination in PR1 areas | Y |  |  |  |  | No | PR1 | MoH
3.1.4n | 4 | Coordination and Partnership development | Community message dissemination in PR2 areas | Y |  |  |  |  | No | PR2 | FBO
3.1.5 | 3 | BCC: Community outreach | Trainings of ASHA, Volunteers, concerned medical/paramedical/program/project personnel, at various levels | N |  |  |  |  | No | PR2 | FBO
3.1.6 | 3 | BCC: Community outreach | M&E of BCC | [5 empty] | No | PR1 | MoH
3.2.1 | 3 | BCC: mass media | Regional workshop for consolidating/fine tuning BCC strategy and operational plan, tools (Mass Media) based on knowledge, materials with NVBDCP) | N |  |  |  |  | No | PR1 | MoH
3.2.2 | 3 | BCC: mass media | Workshop at district level for local adaptation of mass media messages , materials (radio) | N |  |  |  |  | No | PR2 | FBO
3.2.3 | 3 | BCC: mass media | Dubbing of mass media messages in the local languages | N |  |  |  |  | No | PR1 | MoH
3.2.4 | 3 | BCC: mass media | BCC - mass media implementation - skit/jingle on Radio | N |  |  |  |  | No | PR1 | MoH
3.2.5 | 3 | BCC: mass media | M&E of BCC | Detailed under Objective 4. SDA: HSS: Human resources (training/capacity building)
4.1.1 | 4 | HSS: Human resources- Health Work Force | Recruitment of Teams for Technical & Management assistance , M & E assistance ,planning and administration assistance at national , regional , state , district levels
4.1.1a | 4 | HSS: Human resources- Health Work Force | TA through WHO to PR1 at national level ( refer to annexure worksheet) | N |  |  |  |  | No | PR1 | MoH
4.1.1b | 4 | HSS: Human resources- Health Work Force | National level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR1
i | 4 | HSS: Human resources- Health Work Force | Finance & Accounts officer (1) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | Accounts assistant (1) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Computer Programmer--NAMMIS, software, hardware (1) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | Statistician (1) | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | Secretarial Assistants (3) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | Data entry operators (2) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-Laptop with all necessary software and data card(5) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and equipment - Desktop with all with all necessary software and broadband connection (5) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Furniture etc.. | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Office infrastructure and Equipment -office automation unit -- printer(1), copier (1), fax (1) , Scanner (1) | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Office Expenses - Documentation and printing | N |  |  |  |  | No | PR1 | MoH
xii | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other equipments | N |  |  |  |  | No | PR1 | MoH
4.1.1c | 4 | HSS: Human resources- Health Work Force | Regional Resource Team with PR1
i | 4 | HSS: Human resources- Health Work Force | Specialist--Public Health (1) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | Specialist--Entomology (1) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Specialist--M&E/MIS, QA, operations research (1) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | Specialist--BCC, Public Private Partnership (1) | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | Specialist--Training (1) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | Administrative officer (1) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | Accountant (1) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Statistician (1) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Data manager including GIS (1) | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Data entry operator(1) | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant(1) | N |  |  |  |  | No | PR1 | MoH
xii | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR1 | MoH
xiii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-Laptop with all necessary software and data card (5) | N |  |  |  |  | No | PR1 | MoH
xiv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-Desktop with all with all necessary software and broadband connection (2) | N |  |  |  |  | No | PR1 | MoH
xv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment (furniture etc) | N |  |  |  |  | No | PR1 | MoH
xvi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure & Equipment-office automation units--printer(1), copier (1), fax (1) , Scanner (1) ,Telephone with intercom facility (5) | N |  |  |  |  | No | PR1 | MoH
xvii | 4 | HSS: Human resources- Health Work Force | Office expenses--Documentation and printing | N |  |  |  |  | No | PR1 | MoH
xviii | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR1 | MoH
xix | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other equipments | N |  |  |  |  | No | PR1 | MoH
4.1.1d | 4 | HSS: Human resources- Health Work Force | State level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR1
I | 4 | HSS: Human resources- Health Work Force | VBD Project Manager(7) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | M&E / MIS Project Manager(7) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | BCC/PPP Manager(7) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | PSCM manager (7) | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | · Finance and accounts officer (7) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | · Statistical assistant (7) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | · Secretarial Assistant (14) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Laptop with all necessary software and data card | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -Desktop with all with all necessary software and broadband connection (3) | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) Telephone with intercom facility (5) | N |  |  |  |  | No | PR1 | MoH
xii | 4 | HSS: Human resources- Health Work Force | Office Expenses - Documentation and printing | N |  |  |  |  | No | PR1 | MoH
xiii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment (furniture etc...) | N |  |  |  |  | No | PR1 | MoH
xiv | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR1 | MoH
xv | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other office equipments | N |  |  |  |  | No | PR1 | MoH
4.1.1e | 4 | HSS: Human resources- Health Work Force | District level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR1
i | 4 | HSS: Human resources- Health Work Force | District VBD (Malaria) Project Officer (86) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | MTS (258) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant cum Data entry operator (86) | N |  |  |  |  | No | PR1 | MoH
iv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Mobility Provision | N |  |  |  |  | No | PR1 | MoH
v | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR1 | MoH
vi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure - Laptop with all necessary software and data card (86) | N |  |  |  |  | No | PR1 | MoH
vii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Desktop with all with all necessary software and broadband connection (86) | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment --Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) Telephone with intercom facility (1) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office Expense - Documentation and printing | N |  |  |  |  | No | PR1 | MoH
viii | 4 | HSS: Human resources- Health Work Force | Office infrastructure and Equipment ( furniture..) | N |  |  |  |  | No | PR1 | MoH
ix | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR1 | MoH
x | 4 | HSS: Human resources- Health Work Force | Office Expenses -- Maintenance of IT equipment and other equipment | N |  |  |  |  | No | PR1 | MoH
xi | 4 | HSS: Human resources- Health Work Force | Lab Technician (62) | N |  |  |  |  | No | PR1 | MoH
4.1.1f | 4 | HSS: Human resources- Health Work Force | Sentinel Surveillance Team
i | 4 | HSS: Human resources- Health Work Force | Nodal Officer at Sentinel Site (13) | N |  |  |  |  | No | PR1 | MoH
ii | 4 | HSS: Human resources- Health Work Force | Lab Technician at sentinel Site (13) | N |  |  |  |  | No | PR1 | MoH
iii | 4 | HSS: Human resources- Health Work Force | Office infrastructure and Equipments and Office expenses | N |  |  |  |  | No | PR1 | MoH
4.1.1g | 4 | HSS: Human resources- Health Work Force | National level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR2 & SRs
I | 4 | HSS: Human resources- Health Work Force | Team leader (1) | N |  |  |  |  | No | PR2 | FBO
ii | 4 | HSS: Human resources- Health Work Force | Manager—Technical (1) | N |  |  |  |  | No | PR2 | FBO
iii | 4 | HSS: Human resources- Health Work Force | Manager—Grant (1) | N |  |  |  |  | No | PR2 | FBO
iv | 4 | HSS: Human resources- Health Work Force | Manager Short Term --GFATM (3) [Short term--60 days in a year] | N |  |  |  |  | No | PR2 | FBO
v | 4 | HSS: Human resources- Health Work Force | Expert—M&E (1) | N |  |  |  |  | No | PR2 | FBO
vi | 4 | HSS: Human resources- Health Work Force | · Expert--MIS (1) [Part Time--120 days in a year] | N |  |  |  |  | No | PR2 | FBO
vii | 4 | HSS: Human resources- Health Work Force | · Expert—Training (1) | N |  |  |  |  | No | PR2 | FBO
viii | 4 | HSS: Human resources- Health Work Force | Technical Expert (2) [Short Term --240 days in a year] | N |  |  |  |  | No | PR2 | FBO
ix | 4 | HSS: Human resources- Health Work Force | Communication officer (1) | N |  |  |  |  | No | PR2 | FBO
x | 4 | HSS: Human resources- Health Work Force | Finance and accounts officer (1) | N |  |  |  |  | No | PR2 | FBO
xi | 4 | HSS: Human resources- Health Work Force | Data and documentation officer (4) | N |  |  |  |  | No | PR2 | FBO
xii | 4 | HSS: Human resources- Health Work Force | Data entry operator (2) | N |  |  |  |  | No | PR2 | FBO
xiii | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant (4) | N |  |  |  |  | No | PR2 | FBO
xiv | 4 | HSS: Human resources- Health Work Force | Travel etc (inter-city within country) for Team leader (once in three months) | N |  |  |  |  | No | PR2 | FBO
xv | 4 | HSS: Human resources- Health Work Force | Travel (out station--inter-city/inter-state within country) for project staff (2 consultants at a time once a month) | N |  |  |  |  | No | PR2 | FBO
xvi | 4 | HSS: Human resources- Health Work Force | Travel (international) for attending international meeting, workshop etc of GFATM and its partners 2 person X 2 per year | N |  |  |  |  | No | PR2 | FBO
xvii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Laptop with all necessary software and data card (5) | N |  |  |  |  | No | PR2 | FBO
xviii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment - Desktop with all with all necessary software and broadband connection (5) | N |  |  |  |  | No | PR2 | FBO
xix | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment (furniture etc..) and Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) and telephone facilities | N |  |  |  |  | No | PR2 | FBO
xx | 4 | HSS: Human resources- Health Work Force | Office Expenses --Documentation and printing | N |  |  |  |  | No | PR2 | FBO
xxi | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables etc. | N |  |  |  |  | No | PR2 | FBO
xxii | 4 | HSS: Human resources- Health Work Force | Office Expenses -- Maintenance of IT equipment and other office equipment | N |  |  |  |  | No | PR2 | FBO
4.1.1h | 4 | HSS: Human resources- Health Work Force | Regional level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR2 & SRs
I | 4 | HSS: Human resources- Health Work Force | Project Manager (4—one each for PR2, SR1, SR2, SR3) | N |  |  |  |  | No | PR2 | FBO
ii | 4 | HSS: Human resources- Health Work Force | Project Officer (4—one each for PR2, SR1, SR2, SR3) | N |  |  |  |  | No | PR2 | FBO
iii | 4 | HSS: Human resources- Health Work Force | Finance & Accounts manager (4) | N |  |  |  |  | No | PR2 | FBO
iv | 4 | HSS: Human resources- Health Work Force | Logistics & SCM manager (1) | N |  |  |  |  | No | PR2 | FBO
v | 4 | HSS: Human resources- Health Work Force | M&E/MIS manager (1) | N |  |  |  |  | No | PR2 | FBO
vi | 4 | HSS: Human resources- Health Work Force | BCC/PPP manager (4) | N |  |  |  |  | No | PR2 | FBO
vii | 4 | HSS: Human resources- Health Work Force | Capacity building/Training manager (1) | N |  |  |  |  | No | PR2 | FBO
viii | 4 | HSS: Human resources- Health Work Force | Data and documentation officer (4) | N |  |  |  |  | No | PR2 | FBO
ix | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant cum Data entry operator (8) | N |  |  |  |  | No | PR2 | FBO
x | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR2 | FBO
xi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -- Laptop with all necessary software and data card (15) | N |  |  |  |  | No | PR2 | FBO
xii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -- Desktop with all with all necessary software and broadband connection (15) | N |  |  |  |  | No | PR2 | FBO
xiii | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment (furniture.. ) , Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1) Office automation units (5)and Telephone with intercom facility | N |  |  |  |  | No | PR2 | FBO
xiv | 4 | HSS: Human resources- Health Work Force | Office Expenses --Documentation and printing | N |  |  |  |  | No | PR2 | FBO
xv | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR2 | FBO
xvi | 4 | HSS: Human resources- Health Work Force | Office Expenses - Maintenance of IT equipment and other office equipments | N |  |  |  |  | No | PR2 | FBO
4.1.1i | 4 | HSS: Human resources- Health Work Force | District level team for Technical & Management assistance , M & E assistance ,planning and administration assistance with PR2 & SRs
i | 4 | HSS: Human resources- Health Work Force | Project Officer (24) | N |  |  |  |  | No | PR2 | FBO
ii | 4 | HSS: Human resources- Health Work Force | Secretarial Assistant cumData entry operator (24) | N |  |  |  |  | No | PR2 | FBO
iii | 4 | HSS: Human resources- Health Work Force | Travel ( hiring of vehicle as needed) | N |  |  |  |  | No | PR2 | FBO
iv | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment -- Laptop with all necessary software and data card | N |  |  |  |  | No | PR2 | FBO
v | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment --\Desktop with all with all necessary software and broadband connection | N |  |  |  |  | No | PR2 | FBO
vi | 4 | HSS: Human resources- Health Work Force | Office Infrastructure and Equipment furniture etc , Office automation units (1)--printer(1), copier (1), fax (1) , Scanner (1), Telephone with intercom facility | N |  |  |  |  | No | PR2 | FBO
vii | 4 | HSS: Human resources- Health Work Force | Office Expenses--Documentation and printing | N |  |  |  |  | No | PR2 | FBO
viii | 4 | HSS: Human resources- Health Work Force | Office expenses--space, water, electricity, consumables and rent etc.. | N |  |  |  |  | No | PR2 | FBO
ix | 4 | HSS: Human resources- Health Work Force | Office Expense - Maintenance of IT equipment and other office equipment | N |  |  |  |  | No | PR2 | FBO
4.2.1 | 4 | HSS : Information System (M&E / MIS) | Regional consultation for consolidation and fine tuning of one M&E plan | N |  | ` |  |  | No | PR1 | MoH
4.2.2a | 4 | HSS : Information System (M&E / MIS) | Integration of M&E Plan and performance monitoring for PR2 : consultation | N |  |  |  |  | No | PR2 | FBO
4.2.2b | 4 | HSS : Information System (M&E / MIS) | Development of MIS for PR2 performance reporting analysis and feed back to GFATM / Stakeholders | [5 empty] | No | PR1 | MoH
4.2.3a | 4 | HSS : Information System (M&E / MIS) | Printing and disseminations of M&E / MIS plan , guidelines , formats , check list to PR1 stakeholders | N |  |  |  |  | No | PR1 | MoH
4.2.3b | 4 | HSS : Information System (M&E / MIS) | Printing and disseminations of M&E / MIS plan , guidelines , formats , check list to PR2 stakeholders | N |  |  |  |  | No | PR2 | FBO
4.2.4 | 4 | HSS : Information System (M&E / MIS) | Training of M&E | N |  |  |  |  | No | PR2 | FBO
4.2.5a | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 national team in PR1 areas | [5 empty] | No | PR1 | MoH
4.2.5b | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 by Regional team in PR1 areas | N |  |  |  |  | No | PR1 | MoH
4.2.5c | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 states team in PR1 areas | N |  |  |  |  | No | PR2 | FBO
4.2.5d | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR1 district team - VBD project officer / MTS in PR1 areas | N | [5 empty] | PR2 | FBO
4.2.5e | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR2 national team in PR2 areas | N | [5 empty] | PR2 | FBO
4.2.5f | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR2 by Regional team in PR2 areas | N |  |  |  |  | No | PR1 | MoH
4.2.5g | 4 | HSS : Information System (M&E / MIS) | Supervision and Monitoring visits by PR2 district team in PR2 areas | N |  |  |  |  | No | PR1 | MoH
4.2.6a | 4 | HSS : Information System (M&E / MIS) | Annual planning and review meeting at national level with regional and state teams and other stakeholders -- PR1 | N |  |  |  |  | No | PR1 | MoH
4.2.6b | 4 | HSS : Information System (M&E / MIS) | Annual Planning and review meeting at state level with districts , other stakeholders -- PR1 | N |  |  |  |  | No | PR1 | MoH
4.2.6c | 4 | HSS : Information System (M&E / MIS) | Quarterly planning and review meeting at districts level with stakeholders -- PR1 | N |  |  |  |  | No | PR1 | MoH
4.2.6d | 4 | HSS : Information System (M&E / MIS) | Annual Planning and Review Meeting at National level with regional ,SRs ,other stakeholders -- PR2 | N |  |  |  |  | No | PR2 | FBO
4.2.6e | 4 | HSS : Information System (M&E / MIS) | Quarterly planning and Review Meeting at districts level with Stakeholders -- PR2 | N |  |  |  |  | No | PR2 | FBO
4.2.7 | 4 | HSS : Information System (M&E / MIS) | Lot Quality Assurance Sampling (LQAS) | N | [5 empty] | PR1 | MoH
4.2.8 | 4 | HSS : Information System (M&E / MIS) | Large Scale Population and house hold survey | N |  |  |  |  | No | PR1 | MoH
4.2.9 | 4 | HSS : Information System (M&E / MIS) | Evaluation by Independent agency | N |  |  |  |  | No | PR1 | MoH
4.2.10 | 4 | HSS : Information System (M&E / MIS) | Joint programme review by Mission | N |  |  |  |  | No | PR1 | MoH
4.2.11 | 4 | HSS : Information System (M&E / MIS) | Production of annual programme report and dissemination to stakeholders | N |  |  |  |  | No | PR1 | MoH
4.2.12 | 4 | HSS : Information System (M&E / MIS) | Operational Research | N |  |  |  |  | No | PR1 | MoH
4.2.13a | 4 | HSS : Information System (M&E / MIS) | Sentinel Surveillance- Training of Medical & para medical personnel | [6 empty] | PR1 | MoH
4.2.13b | 4 | HSS : Information System (M&E / MIS) | Sentinel Surveillance support for reporting of severe cases and deaths | [5 empty] | No | PR1 | MoH
4.3.1 | 4 | Coordination and Partnership development | National level consultation on coordination and partnership building with other departments/ Porgramme of MOHFW , #n health ministries / departments , NGO / FBO , Private sector , etc. | N |  |  |  |  | No | PR1 | MoH
4.3.2 | 4 | Coordination and Partnership development | One on one meeting with armed and para military forces , other non health ministries / dep't , municipal corporations , private sector ,PSU, NGO / FBO for partnership and MOU under PPP | N |  |  |  |  | No | PR1 | MoH
4.3.3 | 4 | Coordination and Partnership development | Inter Ministerial meeting on observance of anti-malaria month | N | [5 empty] | PR1 | MoH
4.3.4 | 4 | Coordination and Partnership development | Regional level workshop on coordination and partnership building with non health ministries / departments ,PSU , NGO / FBO , Private sector , etc. | N |  |  |  |  | No | PR1 | MoH
4.3.5 | 4 | Coordination and Partnership development | Inter Country Meeting on Border Malaria Issues | N |  |  |  |  | No | PR1 | MoH
4.3.6 | 4 | Coordination and Partnership development | Development & dissemination of newsletters | N |  |  |  |  | No | PR2 | FBO
5.1.1a | 5 | HSS: Human resources Training / Capacity Building | Induction Training of National , State level teams of PR1 at national level | N |  |  |  |  | No | PR1 | MoH
5.1.1b | 5 | HSS: Human resources Training / Capacity Building | Induction Training of National , Regional level teams of PR2 & SRs at national level | N |  |  |  |  | No | PR2 | FBO
5.1.1c | 5 | HSS: Human resources Training / Capacity Building | Induction Training of District level teams of PR2 & SRs at regional level | N |  |  |  |  | No | PR2 | FBO
5.1.2a | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of National , State level teams of PR1 at national level | N |  |  |  |  | No | PR1 | MoH
5.1.2b | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of National , Regional level teams of PR2 & SRs at national level | N |  |  |  |  | No | PR2 | FBO
5.1.2c | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of District level teams of PR2 & SRs at regional level | N |  |  |  |  | No | PR2 | FBO
5.1.3 | 5 | HSS: Human resources Training / Capacity Building | Training of National level programme personnel , consultant with PR1 co-managing GFATM grant on management | N |  |  |  |  | No | PR1 | MoH
5.1.4 | 5 | HSS: Human resources Training / Capacity Building | Induction training of District VBD (Malaria) Project Officer at national level | N |  |  |  |  | No | PR1 | MoH
5.1.5 | 5 | HSS: Human resources Training / Capacity Building | Refresher training of District VBD (Malaria) Project Officer at regional level | N |  |  |  |  | No | PR1 | MoH
5.1.6 | 5 | HSS: Human resources Training / Capacity Building | Induction Training of MTS | N |  |  |  |  | No | PR1 | MoH
5.1.7 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of MTS | N |  |  |  |  | No | PR1 | MoH
5.1.8 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training of Medial Officer from referral health unit on management of severe malaria | N |  |  |  |  | No | PR1 | MoH
5.1.9 | 5 | HSS: Human resources Training / Capacity Building | Training Medical and para medical (LT) personnel in Sentinel surveillance sites on surveillance , data reporting / management | N |  |  |  |  | No | PR1 | MoH
5.1.10 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training for Medical Officers at Block PHC / PHC / CHC ; sub district health unit with PR2 | N |  |  |  |  | No | PR1 | MoH
5.1.11 | 5 | HSS: Human resources Training / Capacity Building | Refresher Training for Lab. Technicians | N |  |  |  |  | No | PR1 | MoH
5.1.12a | 5 | HSS: Human resources Training / Capacity Building | Revisiting existing training modules for ASHA / Volunteers , customization, translationin | N |  |  |  |  | No | PR2 | FBO
5.1.12b | 5 | HSS: Human resources Training / Capacity Building | Replication and dissemination of training modules for ASHA / Volunteers | N |  |  |  |  | No | PR2 | FBO
5.1.13 | 5 | HSS: Human resources Training / Capacity Building | Training of ASHA / Volunteer | Y |  |  |  |  | No | PR2 | FBO
5.1.14a | 5 | HSS: Human resources Training / Capacity Building | Revisiting, customization, translation existing guidelines and development of training modules for private sector service provider | N |  |  |  |  | No | PR2 | FBO
5.1.14b | 5 | HSS: Human resources Training / Capacity Building | Replication and dissemination of existing modules for private sector service providers training at regional level | N |  |  |  |  | No | PR2 | FBO
5.1.15a | 5 | HSS: Human resources Training / Capacity Building | Mapping and training private sector service providers according to qualifications at block level in PR1 and PR2 areas | N |  |  |  |  | No | PR2 | FBO
5.1.15b | 5 | HSS: Human resources Training / Capacity Building | Mapping and training private sector service providers according to qualifications at District level in PR1 and PR2 areas | N |  |  |  |  | No | PR2 | FBO